## Sheet1
RISK MATRIX Instructions: For your project, complete the risk matrix as we've practiced in class for at least 10 risks (A-J). Once complete, map out those risks onto a risk chart similar to the one shown below. |  |  |  | Orion Down
Risk # | What is the risk? | Severity Rank (1-10) | Probability Rank (1-10) | What are you going to do about it? | When are you going to get that done? | Severity Rank after Mitigation (1-10) | Probability Rank after Mitigation (1-10)
1 | Run out of time | 10 | 5 | Keep a schedule | Immediately | 10 | 2
2 | Run out of time (feature creep) | 10 | 5 | Maintain scope | Throughout | 10 | 3
3 | Run out of time (learning curve) | 10 | 5 | Self-teaching | Throughout | 10 | 3
4 | Connectivity issues | 6 | 7 | Q/A testing | End of project | 6 | 1
5 | Unintuitive | 7 | 8 | Q/A | End of project | 4 | 3
6 | Unintuitive | 7 | 8 | Documentation | End of project | 4 | 3
7 | Unintuitive | 7 | 8 | Cirriculum research | End of project | 4 | 3
8 | Unintuitive | 7 | 8 | Pre-class | End of project | 4 | 3
9 | Unintuitive | 7 | 8 | Survey | Before Development | 4 | 3
10 | Modules too difficult | 7 | 3 | Q/A testing | End of project | 5 | 3
11 | Does not function correctly | 10 | 10 | Q/A testing | Throughout | 2 | 2
12