## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Design Door | 5
Shape/Size | 2 | Dettman |  | 0.5
Made of ? | 2 | Norris/
Construct Door | 1 | Baca |  | 3
Arduino Learning
Learning | 1 | Aragon | in Prograess | 3
Learning | 1 | Godfrey | in Prograess | 3
Learning | 1 | Rozneck | in Prograess | 3
Main Sanner
Design/3d model | 3 | Ocean/Cooper/Ellett | In Progress | 3
Build/print model | 2 | Leonard | Waiting | 3
Q/A Test | 1 | Ocean/Cooper/Ellett | Waiting | 0.5
Mock Install at CLC | 1 | Ocean/Martinez | Waiting | 1.5
TOTAL |  |  |  | 20.5 | 0 | 0 | 0 | 0 | 0 | 0

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0