## EX - Sprint Planning Template
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Product Release |  |  | Alex B. |  | 2028-01-16 | 2028-04-21 | 35% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 |  | Alex B. |  | 2028-01-16 | 2028-02-15 | 31
Yes | Feature 1 |  | Frank C. |  | 2028-01-16 | 2028-02-02 | 18 | Complete | High
No | Feature 2 |  | Jacob S. |  | 2028-01-31 | 2028-02-05 | 6 | In Progress | Medium
| Feature 3 |  | Jacob S. |  | 2028-02-05 | 2028-02-15 | 11 | Not Started | Low
| SPRINT 2 |  | Jacob S. |  | 2028-01-22 | 2028-02-25 | 35
| Feature 1 |  | Alex B. |  | 2028-01-22 | 2028-01-29 | 8 | Overdue
| Feature 2 |  | Frank C. |  | 2028-01-28 | 2028-01-31 | 4 | Needs Review
| Feature 3 |  | Shari W. |  | 2028-01-29 | 2028-02-25 | 28 | Approved
| SPRINT 3 |  | Shari W. |  | 2028-02-28 | 2028-03-16 | 18
| Feature 1 |  | Alex B. |  | 2028-02-28 | 2028-03-01 | 3 | On Hold
| Feature 2 |  | Kennedy K. |  | 2028-02-28 | 2028-03-04 | 6
| Feature 3 |  | Jacob S. |  | 2028-03-01 | 2028-03-16 | 16
| SPRINT 4 |  | Jacob S. |  | 2028-03-16 | 2028-04-16 | 32
| Feature 1 |  | Jacob S. |  | 2028-03-16 | 2028-03-17 | 2
| Feature 2 |  | Jacob S. |  | 2028-03-18 | 2028-03-20 | 3
| Feature 3 |  | Alex B. |  | 2028-03-24 | 2028-04-16 | 24
| SPRINT 5 |  | Frank C. |  | 2028-03-24 | 2028-04-21 | 29
| Feature 1 |  | Shari W. |  | 2028-03-24 | 2028-03-26 | 3
| Feature 2 |  | Shari W. |  | 2028-03-26 | 2028-04-05 | 11
| Feature 3 |  | Kennedy K. |  | 2028-04-06 | 2028-04-21 | 16

## BLANK - Sprint Planning
SPRINT PLANNING TEMPLATE
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
[7 empty] | 0% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
SPRINT 1
Feature 1
Feature 2
Feature 3
SPRINT 2
Feature 1
Feature 2
Feature 3
SPRINT 3
Feature 1
Feature 2
Feature 3
SPRINT 4
Feature 1
Feature 2
Feature 3
SPRINT 5
Feature 1
Feature 2
Feature 3
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold